## Slide 1: Tempus Project 517119-TEMPUS-1-2011-RS-TEMPUS-SMGR DEVELOPMENT OF CAREER GUIDANCE AIMED AT IMPROVING HIGHER EDUCATION IN SERBIA
Notes: 1

## Slide 2: New Tempus project coordinated by University of Belgrade (2011-2013) wider objective: DEVELOPMENT OF CAREER GUIDANCE AIMED AT IMPROVING HIGHER EDUCATION IN SERBIA Specific objectives: 1) Development of Services for Career Information, Guidance and Education aiming to increase youth employability, 2) Enabling wider accessibility and variety of programs in Career guidance at Higher Education Institutions (HEI), 3) Raising the level of recognizing importance of Career Guidance by the policy makers and other stake holders and 4) Development of Career Guidance and Counseling (CGC) Program for Young People between the Ages of 19 and 30 (students) and Мethodology for CGC Centres of HEI

## Slide 3: Careers project Consortium
3 EU partners / UK, Italy, Poland
2 ministries / Education and Science and Youth and Sport
5 Serbian universities / Belgrade, Novi Sad, Nis, Kragujevac, Singidunum
Student Conference of Universities of Serbia
3 non academic institutions

## Slide 4
Through project activities it is intended to:
build the System of career guidance at university level in Serbia, according to the priorities that define the new paradigm of career guidance – lifelong guidance:
the centrality of the student in the provision of career services,
the need to refocus provision to develop the skills of individuals to manage their career and learning,
widen the access to services and improve their quality
Beneficiaries of the project outcomes are:
  students,
  universities,
  academic staff,
  employers and
  policy makers

## Slide 5: First year of the project
Work package 4 – Cooperation with employers
Finished analysis and prepared document that represents examples of good practices of cooperation with employers – at European and national level
Round table 13th of June 2012 at University of Novi Sad on cooperation between academic staff and employers – presentation of best EU practices and recommendations for improving existing models of cooperation between academic staff and employers aimed at enhancing student employability

## Slide 6
Work package 5 – Strengthening capacities
questionnaires were sent to all members of university teams to gain insight into the needs of employees for further training and improvement of university career centers at universities in Serbia and define a training plan
universities in Serbia have prepared texts related to the recording situation and perspectives of development of career guidance at universities
texts are published in the publication "Career guidance at universities in Serbia”
On 16th of March 2012 National workshop „Current state and perspectives of career guidance at universities in Serbia” was held at University of Belgrade where the aforementioned publication was presented; two panel discussions related to the improvement of career centers and the importance of establishing a network of centers for career guidance and counseling students
Training plan created by university centers forwarded to the UK partners
In period between 7-15.05. 2012 University of Swansea organized and realized training for domestic university partners.The training was attended by a representative of the Ministry of Youth and Sport.

## Slide 7
Work package 6 – National Programme and Methodology for CGC
A group of experts from partner institutions was formed and two working groups will continue to engage in the development of standards of career guidance at the university in Serbia in accordance with the National Strategy for Career Guidance and Counseling
Initial meeting on the Careers project’s Work Package 6

## Slide 8
Work package 7 - Quality control
During the first working meeting of partners the Quality Committee was formed consisting of representatives from several partner institutions / BOS, Ministry of Youth, University of Nis, University of Belgrade, SKONUS /
first draft of plan for quality control of project activities was composed in February
quality control plan adopted by the members of the Board in April /in early May forwarded to all partners in the project / contact persons

## Slide 9
Work package 8 – Dissemination of project activities
created logo and promotional brochure of the project
developed and implemented the project website Careers and registered in the academic domain www.careers.ac.rs / constantly update of portal content is done by employees of the University of Nis and Belgrade
created mailing list for disseminating information related to the project
project activities are presented outside the consortium partners / SCC, Belgrade and BAYHOST Donauforum, Regensburg, Germany /

## Slide 10
Work package 9 – Sustainability
first steps are made towards establishing a network of career centers as non-government organization; Constituent Assembly was held on 18.04.2012. and all necessary documents /statute of association, founding act, minutes .... / are prepared for formal procedure for registration of Akcent

## Slide 11
Work package 10 – Management
On 30 and 31.01. 2012. the first gathering of partners working on a project was held at the University of Belgrade, where all partners had the opportunity to introduce themselves and get better acquainted with the project, their roles and responsibilities on the project, budget for the project and the rules relating to financial reporting; the first meeting of Steering Committee was held, and a draft of Consortium contract was presented.
plan of project activities for the first year budget and the budgets for specific budget lines and categories of costs for all partners
project funds have been transferred to Partners in accordance with its project activities for the first nine months; Partners are providing narrative and financial report for the first reporting period

## Slide 12
(DEV)1. Information for students
Developing a system of organized and accessible career information relevant for university students
(DEV)2. Information for employers
Developing a system of organized and accessible career information relevant for employers
(DEV)3. Cooperation within academic community
Development of cooperation within academic community for greater coverage and accessibility of career information, counselling and education
(DEV)4. Cooperation with employers
Greater participation of employers in the activities of universities aiming to improving graduates employability and their career management skills
(DEV)5. Strengthening capacities
Strengthening capacities of University Career Centres
(DEV)6. National Programme and Methodology for CGC
National Programme for Career Guidance and Counselling and the Methodology for the age group 19 to 30

## Slide 13
University of Belgrade
Centre for Career Development and Student Counselling
Studentski trg 1, Belgrade, Serbia
www.razvojkarijere.bg.ac.rs
centar@razvokarijere.bg.ac.rs